## Invoices (hidden)
Total | [5 empty] | 1865516.2764 | 1804280.6038 | 12996.9232 | 1817277.527 | 272620.6998 | 2089898.2269
ID | Invoice Date | EOMONTH | Invoice ID | Contractor | Description | Contract Amt. (NET + CNPAIA) (€) | NET (€) | CNPAIA (€) | Invoiced Amt. (NET + CNPAIA) (€) | VAT Invoiced | Gross Invoiced Amt. (€) | Contract Approved? | Invoice Received? | Invoice Approved | Approved by (UHG/Michiel) | Paid?
1 | 2025-02-28 | 2025-02-28 | 2003066 | Stylt | The Usual Hotel Corona Competition+ Travel costs | 4000 | 4000 | 0 | 4000 | 0 | 4000 | 1 | 1 | 1 | 1 | 1 | 0
2 | 2025-03-13 | 2025-03-31 | 2025/072 | Joi-Design | Interior design planning services | 2500 | 2500 | 0 | 2500 | 0 | 2500 | 1 | 1 | 1 | 1 | 1 | 0
3 | 2025-03-29 | 2025-03-31 | n.9/001 | Rizoma | Renovation of Hotel Corona-Interior Contest | 2600 | 2500 | 100 | 2600 | 572 | 3172 | 1 | 1 | 1 | 1 | 1 | 0
4 | 2025-05-30 | 2025-05-31 | VMI25_00270 | Artelia | Project Management | 29200 | 29200 | 0 | 29200 | 6424 | 35624 | 1 | 1 | 1 | 1 | 1 | 0
5 | 2025-05-30 | 2025-05-31 | VMI25_00270 | Artelia | Construction Management | 8000 | 8000 | 0 | 8000 | 1760 | 9760 | 1 | 1 | 1 | 1 | 1 | 0
6 | 2025-05-30 | 2025-05-31 | VMI25_00270 | Artelia | Multidisciplinary Engineering Design | 28080 | 27000 | 0 | 27000 | 5940 | 32940 | 1 | 1 | 1 | 1 | 1 | 0
7 | 2025-06-13 | 2025-06-30 | VMI25_00444 | Artelia /Stylt | Phase 1 - 4 | 76240 | 76240 | 0 | 76240 | 16772.8 | 93012.8 | 1 | 1 | 1 | 1 | 1 | 0
8 | 2025-06-30 | 2025-06-30 | VMI25_00356 | Artelia | Project Management | 11426.087 | 11350.44 | 0 | 11350.44 | 2497.0968 | 13847.5368 | 1 | 1 | 1 | 1 | 1 | 0
9 | 2025-06-30 | 2025-06-30 | VMI25_00356 | Artelia | Construction Management | 3130.4348 | 3304.35 | 0 | 3304.35 | 726.957 | 4031.307 | 1 | 1 | 1 | 1 | 1 | 0
10 | 2025-06-30 | 2025-06-30 | VMI25_00356 | Artelia | Multidisciplinary Engineering Design | 84240 | 76950 | 3078 | 80028 | 17606.16 | 97634.16 | 1 | 1 | 1 | 1 | 1 | 0
11 | 2025-06-30 | 2025-06-30 | VMI25_00356 | Artelia | BREEAM Consultancy | 2600 | 2375 | 95 | 2470 | 543.4 | 3013.4 | 1 | 1 | 1 | 1 | 1 | 0
12 | 2025-07-14 | 2025-07-31 | 146 | Gaia Group | Rilievi Laser Scanner 3D, modellazione 3D Piano Terra e 2D | 16000 | 16000 | 0 | 16000 | 3520 | 19520 | 1 | 1 | 1 | 1 | 1 | 0
13 | 2025-08-05 | 2025-08-31 | 3000083 | HC /Stylt | Travel Costs | 6298 | 6298 | 0 | 6298 | 0 | 6298 | 1 | 1 | 1 | 1 | 1 | 0
14 | 2025-08-17 | 2025-08-31 | 8-2025-FE | Cinquerosso Arte | Artistic statuette sample | 85 | 85 | 0 | 85 | 18.7 | 103.7 | 1 | 1 | 1 | 1 | 0 | 0
15 | 2025-08-20 | 2025-08-31 | - | Municipality_VVF | Comune di Firenze | 504 | 504 | 0 | 504 | 0 | 504 | 1 | 1 | 1 | 1 | 1 | 0
16 | 2025-08-29 | 2025-08-31 | VMI25_00445 | Artelia | Multidisciplinary Engineering Design | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
17 | 2025-09-08 | 2025-09-30 | 3000103 | HC /Stylt | Travel Costs | 4036 | 4036 | 0 | 4036 | 0 | 4036 | 1 | 1 | 1 | 1 | 1 | 0
18 | 2025-09-16 | 2025-09-30 | 075_2025 | Sese | Mock up room n.01 | 14046 | 14046 | 0 | 14046 | 3090.12 | 17136.12 | 1 | 1 | 1 | 1 | 0 | 0
19 | 2025-09-17 | 2025-09-30 | 3000105 | HC /Stylt | Extra Costs | 6120 | 6120 | 0 | 6120 | 0 | 6120 | 1 | 1 | 1 | 1 | 0 | 0
20 | 2025-09-22 | 2025-09-30 | VMI25_00510 | Artelia /Stylt | Phase 1 - 4 | 57180 | 57180 | 0 | 57180 | 12579.6 | 69759.6 | 1 | 1 | 1 | 1 | 1 | 0
21 | 2025-09-22 | 2025-09-30 | VMI25_00509 | Artelia /Stylt | Phase 1 - 4 | 38120 | 38120 | 0 | 38120 | 8386.4 | 46506.4 | 1 | 1 | 1 | 1 | 1 | 0
22 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | Project Management | 11426.087 | 11426.087 | 0 | 11426.087 | 2513.7391 | 13939.8261 | 1 | 1 | 1 | 1 | 1 | 0
23 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | Project Management | 11426.087 | 11426.087 | 0 | 11426.087 | 2513.7391 | 13939.8261 | 1 | 1 | 1 | 1 | 1 | 0
24 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | Project Management | 0 | 0 | 0 | 0 | 0.076522 | 0.076522 | 1 | 1 | 1 | 1 | 1 | 0
25 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | Construction Management | 3130.4348 | 3130.4348 | 0 | 3130.4348 | 688.6957 | 3819.1304 | 1 | 1 | 1 | 1 | 1 | 0
26 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | Construction Management | 3130.4348 | 3130.4348 | 0 | 3130.4348 | 688.6957 | 3819.1304 | 1 | 1 | 1 | 1 | 1 | 0
27 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | Construction Management | 0 | 0 | 0 | 0 | 2513.7391 | 2513.7391 | 1 | 1 | 1 | 1 | 1 | 0
28 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | Multidisciplinary Engineering Design | 84240 | 81000 | 3240 | 84240 | 18532.8 | 102772.8 | 1 | 1 | 1 | 1 | 1 | 0
29 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | Multidisciplinary Engineering Design | 0 | 4050 | 162 | 4212 | 926.64 | 5138.64 | 1 | 1 | 1 | 1 | 1 | 0
30 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | ID Coordination | 869.5652 | 869.5652 | 0 | 869.5652 | 191.3043 | 1060.8696 | 1 | 1 | 1 | 1 | 1 | 0
31 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | ID Coordination | 869.5652 | 869.5652 | 0 | 869.5652 | 191.3043 | 1060.8696 | 1 | 1 | 1 | 1 | 1 | 0
32 | 2025-09-22 | 2025-09-30 | VMI25_00511 | Artelia | ID Coordination | 869.5652 | 869.5652 | 0 | 869.5652 | 191.3043 | 1060.8696 | 1 | 1 | 1 | 1 | 1 | 0
33 | 2025-09-30 | 2025-09-30 | VMI25_00516 | Artelia | Project Management | 11426.087 | 11426.087 | 0 | 11426.087 | 2513.7391 | 13939.8261 | 1 | 1 | 1 | 1 | 1 | 0
34 | 2025-09-30 | 2025-09-30 | VMI25_00516 | Artelia | Construction Management | 3130.4348 | 3130.4348 | 0 | 3130.4348 | 688.6957 | 3819.1304 | 1 | 1 | 1 | 1 | 1 | 0
35 | 2025-09-30 | 2025-09-30 | VMI25_00516 | Artelia | Multidisciplinary Engineering Design | 84240 | 81000 | 3240 | 84240 | 18532.8 | 102772.8 | 1 | 1 | 1 | 1 | 1 | 0
36 | 2025-09-30 | 2025-09-30 | VMI25_00516 | Artelia | ID Coordination | 869.5652 | 869.5652 | 0 | 869.5652 | 191.3043 | 1060.8696 | 1 | 1 | 1 | 1 | 1 | 0
37 | 2025-09-30 | 2025-09-30 | VMI25_00516 | Artelia | BREEAM Consultancy | 0 | 125 | 5 | 130 | 28.6 | 158.6 | 1 | 1 | 1 | 1 | 1 | 0
38 | 2025-09-30 | 2025-09-30 | VMI25_00516 | Artelia | BREEAM Consultancy | 10400 | 10000 | 400 | 10400 | 2288 | 12688 | 1 | 1 | 1 | 1 | 1 | 0
39 | 2025-09-30 | 2025-09-30 | B250410 | Contract | Mock up room n.01 | 16716.28 | 16716.28 | 0 | 16716.28 | 3677.5816 | 20393.8616 | 1 | 1 | 1 | 1 | 0 | 0
40 | 2025-10-08 | 2025-10-31 | 3000129 | HC /Stylt | Extra Costs | 5040 | 5040 | 0 | 5040 | 0 | 5040 | 1 | 1 | 1 | 1 | 0 | 0
41 | 2025-10-08 | 2025-10-31 | 3000126 | HC /Stylt | Extra Costs | 720 | 720 | 0 | 720 | 0 | 720 | 1 | 1 | 1 | 1 | 1 | 0
42 | 2025-10-15 | 2025-10-31 | - | Municipality | Comune di Firenze | 16 | 16 | 0 | 16 | 0 | 16 | 1 | 1 | 1 | 1 | 1 | 0
43 | 2025-10-27 | 2025-10-31 | 3000134 | HC /Stylt | Extra Costs | -720 | -720 | 0 | -720 | 0 | -720 | 1 | 1 | 1 | 1 | 1 | 0
44 | 2025-10-28 | 2025-10-31 | - | Municipality_Asl | Comune di Firenze | 1056 | 1056 | 0 | 1056 | 0 | 1056 | 1 | 1 | 1 | 1 | 1 | 0
45 | 2025-10-31 | 2025-10-31 | VMI25_00595 | Artelia | Project Management | 11426.087 | 11426.087 | 0 | 11426.087 | 2513.7391 | 13939.8261 | 1 | 1 | 1 | 1 | 1 | 0
46 | 2025-10-31 | 2025-10-31 | VMI25_00595 | Artelia | Construction Management | 3130.4348 | 3130.4348 | 0 | 3130.4348 | 688.6957 | 3819.1304 | 1 | 1 | 1 | 1 | 1 | 0
47 | 2025-10-31 | 2025-10-31 | VMI25_00595 | Artelia | ID Coordination | 869.5652 | 869.5652 | 0 | 869.5652 | 191.3043 | 1060.8696 | 1 | 1 | 1 | 1 | 1 | 0
48 | 2025-11-04 | 2025-11-30 | 3000143 | HC /Stylt | Extra Costs | 1680 | 1680 | 0 | 1680 | 0 | 1680 | 1 | 1 | 1 | 1 | 1 | 0
49 | 2025-11-13 | 2025-11-30 | FV-25-2267 | TPC | Mock up room n.02 | 5430 | 5430 | 0 | 5430 | 1194.6 | 6624.6 | 1 | 1 | 1 | 1 | 1 | 0
50 | 2025-11-18 | 2025-11-30 | 104_2025 | Sese | Mock up room n.02 | 6122 | 6122 | 0 | 6122 | 1346.84 | 7468.84 | 1 | 1 | 1 | 1 | 0 | 0
51 | 2025-11-19 | 2025-11-30 | - | Municipality_Asl | Comune di Firenze | 278 | 278 | 0 | 278 | 0 | 278 | 1 | 1 | 1 | 1 | 1 | 0
52 | 2025-11-19 | 2025-11-30 | - | Municipality_Asl | Comune di Firenze | 30 | 30 | 0 | 30 | 0 | 30 | 1 | 1 | 1 | 1 | 1 | 0
53 | 2025-11-28 | 2025-11-30 | VMI25_00688 | Artelia /Stylt | Phase 1 - 4 | 9530 | 9530 | 0 | 9530 | 2096.6 | 11626.6 | 1 | 1 | 1 | 1 | 1 | 0
54 | 2025-11-28 | 2025-11-30 | VMI25_00688 | Artelia | Project Management | 11426.087 | 11426.087 | 0 | 11426.087 | 2513.7391 | 13939.8261 | 1 | 1 | 1 | 1 | 1 | 0
55 | 2025-11-28 | 2025-11-30 | VMI25_00688 | Artelia | Construction Management | 3130.4348 | 3130.4348 | 0 | 3130.4348 | 688.6957 | 3819.1304 | 1 | 1 | 1 | 1 | 1 | 0
56 | 2025-11-28 | 2025-11-30 | VMI25_00688 | Artelia | Direzione Lavori | 9360 | 9000 | 360 | 9360 | 2059.2 | 11419.2 | 1 | 1 | 1 | 1 | 1 | 0
57 | 2025-11-28 | 2025-11-30 | VMI25_00688 | Artelia | Health & Safety | 6240 | 6000 | 240 | 6240 | 1372.8 | 7612.8 | 1 | 1 | 1 | 1 | 1 | 0
58 | 2025-11-28 | 2025-11-30 | VMI25_00688 | Artelia | ID Coordination | 869.5652 | 869.5652 | 0 | 869.5652 | 191.3043 | 1060.8696 | 1 | 1 | 1 | 1 | 1 | 0
59 | 2025-12-08 | 2025-12-31 | XXXXXX | HC /Stylt | Travel Costs | 5579.5652 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0
60 | 2025-12-18 | 2025-12-31 | FV-25-2608 | TPC | Mock up room n.02 | 11906.24 | 11906.24 | 0 | 11906.24 | 2619.3728 | 14525.6128 | 1 | 1 | 1 | 1 | 1 | 0
61 | 2025-12-19 | 2025-12-31 | - | Municipality_SCIA | Comune di Firenze | 30 | 30 | 0 | 30 | 0 | 30 | 1 | 1 | 1 | 1 | 1 | 0
62 | 2025-12-30 | 2025-12-31 | VMI25_00752 | Artelia | Project Management | 11426.087 | 11426.087 | 0 | 11426.087 | 2513.7391 | 13939.8261 | 1 | 1 | 1 | 1 | 0 | 0
63 | 2025-12-30 | 2025-12-31 | VMI25_00752 | Artelia | Construction Management | 3130.4348 | 3130.4348 | 0 | 3130.4348 | 688.6957 | 3819.1304 | 1 | 1 | 1 | 1 | 0 | 0
64 | 2025-12-30 | 2025-12-31 | VMI25_00752 | Artelia | Direzione Lavori | 6480 | 6230.76 | 249.2304 | 6479.9904 | 1425.5979 | 7905.5883 | 1 | 1 | 1 | 1 | 0 | 0
65 | 2025-12-30 | 2025-12-31 | VMI25_00752 | Artelia | Health & Safety | 4320 | 4153.84 | 166.1536 | 4319.9936 | 950.3986 | 5270.3922 | 1 | 1 | 1 | 1 | 0 | 0
66 | 2025-12-30 | 2025-12-31 | VMI25_00752 | Artelia | ID Coordination | 869.5652 | 869.5652 | 0 | 869.5652 | 191.3043 | 1060.8696 | 1 | 1 | 1 | 1 | 0 | 0
67 | 2026-01-09 | 2026-01-31 | FV-26-0026 | TPC | Mock up room n.02 | 763.7 | 763.7 | 0 | 763.7 | 168.014 | 931.714 | 1 | 1 | 1 | 1 | 1 | 0
68 | 2026-01-13 | 2026-01-31 | 3000197 | HC /Stylt | Travel Costs | 4854 | 4854 | 0 | 4854 | 0 | 4854 | 1 | 1 | 1 | 1 | 0 | 0
69 | 2026-01-20 | 2026-01-31 | VMI26_00002 | Artelia | Project Management | 45704.3478 | 45704 | 0 | 45704 | 10054.88 | 55758.88 | 1 | 1 | 1 |  | 0 | 0
70 | 2026-01-20 | 2026-01-31 | VMI26_00002 | Artelia | Construction Management | 12521.7391 | 12520 | 0 | 12520 | 2754.4 | 15274.4 | 1 | 1 | 1 |  | 0 | 0
71 | 2026-01-20 | 2026-01-31 | VMI26_00002 | Artelia | ID Coordination | 3478.2609 | 3480 | 0 | 3480 | 765.6 | 4245.6 | 1 | 1 | 1 |  | 0 | 0
72 | 2026-01-22 | 2026-01-31 | XXXX | Municipality_Asl | Comune di Firenze:Pagamenti sportello unico attività produttive | 1288.32 | 1288.32 | 0 | 1288.32 | 0 | 1288.32 | 1 | 1 | 1 | 1 | 1 | 0
73 | 2026-01-30 | 2026-01-31 | 3000216 | HC /Stylt | Signage | 3000 | 3000 | 0 | 3000 | 0 | 3000 | 1 | 1 | 1 | 1 | 0 | 0
74 | 2026-01-30 | 2026-01-31 | 3000217 | HC /Stylt | Art&Props | 10000 | 10000 | 0 | 10000 | 0 | 10000 | 1 | 1 | 1 | 1 | 0 | 0
75 | 2026-01-30 | 2026-01-31 | XXXX | HC /Stylt | Art&Props | 25000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0
76 | 2026-01-30 | 2026-01-31 | XXXX | Protos | Monitoring | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0
77 | 2026-02-04 | 2026-02-28 | 3000231 | HC /Stylt | Extra Costs | 1620 | 1620 | 0 | 1620 | 0 | 1620 | 1 | 1 | 1 | 1 | 0 | 0
78 | 2026-02-04 | 2026-02-28 | 3000232 | HC /Stylt | Extra Costs | 2580 | 2580 | 0 | 2580 | 0 | 2580 | 1 | 1 | 1 | 1 | 0 | 0
79 | 2026-02-27 | 2026-02-28 | - | ENEL | ENEL | 20419.39 | 20442.39 | 0 | 20442.39 | 4497.3258 | 24939.7158 | 1 | 1 | 1 | 1 | 1 | 0
80 | 2026-02-28 | 2026-02-28 | VMI26_00108 | Artelia /Stylt | Phase 1 - 4 | 9530 | 9530 | 0 | 9530 | 2096.6 | 11626.6 | 1 | 1 | 1 |  | 0 | 0
81 | 2026-02-28 | 2026-02-28 | VMI26_00105 | Artelia | Project Management | 11426.087 | 11426 | 0 | 11426 | 2513.72 | 13939.72 | 1 | 1 | 1 |  | 0 | 0
82 | 2026-02-28 | 2026-02-28 | VMI26_00106 | Artelia | Project Management | 11426.087 | 11426 | 0 | 11426 | 2513.72 | 13939.72 | 1 | 1 | 1 |  | 0 | 0
83 | 2026-02-28 | 2026-02-28 | VMI26_00105 | Artelia | Construction Management | 3130.4348 | 3130.65 | 0 | 3130.65 | 688.743 | 3819.393 | 1 | 1 | 1 |  | 0 | 0
84 | 2026-02-28 | 2026-02-28 | VMI26_00106 | Artelia | Construction Management | 3130.4348 | 3130.65 | 0 | 3130.65 | 688.743 | 3819.393 | 1 | 1 | 1 |  | 0 | 0
85 | 2026-02-28 | 2026-02-28 | VMI26_00105 | Artelia | Direzione Lavori | 6480 | 6230.77 | 249.2308 | 6480.0008 | 1425.6002 | 7905.601 | 1 | 1 | 1 |  | 0 | 0
86 | 2026-02-28 | 2026-02-28 | VMI26_00106 | Artelia | Direzione Lavori | 6480 | 6230.77 | 249.2308 | 6480.0008 | 1425.6002 | 7905.601 | 1 | 1 | 1 |  | 0 | 0
87 | 2026-02-28 | 2026-02-28 | VMI26_00105 | Artelia | Health & Safety | 4320 | 4153.85 | 166.154 | 4320.004 | 950.4009 | 5270.4049 | 1 | 1 | 1 |  | 0 | 0
88 | 2026-02-28 | 2026-02-28 | VMI26_00106 | Artelia | Health & Safety | 4320 | 4153.85 | 166.154 | 4320.004 | 950.4009 | 5270.4049 | 1 | 1 | 1 |  | 0 | 0
89 | 2026-02-28 | 2026-02-28 | VMI26_00105 | Artelia | ID Coordination | 869.5652 | 869.34 | 0 | 869.34 | 191.2548 | 1060.5948 | 1 | 1 | 1 |  | 0 | 0
90 | 2026-02-28 | 2026-02-28 | VMI26_00106 | Artelia | ID Coordination | 869.5652 | 869.34 | 0 | 869.34 | 191.2548 | 1060.5948 | 1 | 1 | 1 |  | 0 | 0
91 | 2026-02-28 | 2026-02-28 | XXXX | CO.E.LIVE_GC | GC Works | 11179.1114 | 11179.1114 | 0 | 11179.1114 | 0 | 11179.1114 | 1 | 0 | 0 |  | 0 | 11179.1114
92 | 2026-02-28 | 2026-02-28 | XXXX | CO.E.LIVE_GC | GC Works | 140431.3877 | 140431.3877 | 0 | 140431.3877 | 0 | 140431.3877 | 1 | 0 | 0 |  | 0 | 140431.3877
93 | 2026-02-28 | 2026-02-28 | XXXX | CO.E.LIVE_GC | GC Works | 98551.1332 | 98551.1332 | 0 | 98551.1332 | 0 | 98551.1332 | 1 | 0 | 0 |  | 0 | 98551.1332
94 | 2026-02-28 | 2026-02-28 | XXXX | CO.E.LIVE_GC | GC Works | 19098.92 | 19098.92 | 0 | 19098.92 | 0 | 19098.92 | 1 | 0 | 0 |  | 0 | 19098.92
95 | 2026-02-28 | 2026-02-28 | TD01-19 | CO.E.LIVE_GC | GC Works | 119173.77 | 119173.77 | 0 | 119173.77 | 26218.2294 | 145391.9994 | 1 | 1 | 1 |  | 1 | 0
96 | 2026-02-28 | 2026-02-28 | TD01-19 | CO.E.LIVE_GC | GC Works | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0
97 | 2026-02-28 | 2026-02-28 | TD01-19 | CO.E.LIVE_GC | GC Works | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0
98 | 2026-02-28 | 2026-02-28 | TD01-19 | CO.E.LIVE_GC | GC Works | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0
99 | 2026-02-28 | 2026-02-28 | TD01-19 | CO.E.LIVE_GC | GC Works | 23654.034 | 23654.034 | 0 | 23654.034 | 5203.8875 | 28857.9215 | 1 | 1 | 1 |  | 1 | 0
100 | 2026-03-13 | 2026-03-31 | XXXX | CO.E.LIVE_GC | GC Works | 140739.5026 | 140739.5026 | 0 | 140739.5026 | 0 | 140739.5026 | 1 | 0 | 0 |  | 0 | 140739.5026
101 | 2026-03-31 | 2026-03-31 | VMI26_00134 | Artelia | Project Management | 11426.087 | 11426.14 | 0 | 11426.14 | 0 | 11426.14 | 1 | 1 | 1 |  | 0 | 0
102 | 2026-03-31 | 2026-03-31 | VMI26_00134 | Artelia | Construction Management | 3130.4348 | 3130.56 | 0 | 3130.56 | 0 | 3130.56 | 1 | 1 | 1 |  | 0 | 0
103 | 2026-03-31 | 2026-03-31 | VMI26_00134 | Artelia | Direzione Lavori | 6480 | 6230.77 | 249.2308 | 6480.0008 | 0 | 6480.0008 | 1 | 1 | 1 |  | 0 | 0
104 | 2026-03-31 | 2026-03-31 | VMI26_00134 | Artelia | Health & Safety | 4320 | 4153.85 | 166.154 | 4320.004 | 0 | 4320.004 | 1 | 1 | 1 |  | 0 | 0
105 | 2026-03-31 | 2026-03-31 | VMI26_00134 | Artelia | ID Coordination | 869.5652 | 869.43 | 0 | 869.43 | 0 | 869.43 | 1 | 1 | 1 |  | 0 | 0
106 | 2026-03-31 | 2026-03-31 | TD01-30 | CO.E.LIVE_GC | GC Works | 123448.032 | 123448.032 | 0 | 123448.032 | 40113.7744 | 163561.8064 | 1 | 1 | 1 |  | 0 | 0
107 | 2026-03-31 | 2026-03-31 | TD01-30 | CO.E.LIVE_GC | GC Works | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 |  | 0 | 0
108 | 2026-03-31 | 2026-03-31 | TD01-30 | CO.E.LIVE_GC | GC Works | 38719.287 | 38719.287 | 0 | 38719.287 | 0 | 38719.287 | 1 | 1 | 1 |  | 0 | 0
109 | 2026-03-31 | 2026-03-31 | TD01-30 | CO.E.LIVE_GC | GC Works | 20168.019 | 20168.019 | 0 | 20168.019 | 0 | 20168.019 | 1 | 1 | 1 |  | 0 | 0
110 | 2026-03-31 | 2026-03-31 | TD01-30 | CO.E.LIVE_GC | GC Works | 16545.78 | 16545.78 | 0 | 16545.78 | 3640.0716 | 20185.8516 | 1 | 1 | 1 |  | 0 | 0
111 | 2026-04-24 | 2026-04-30 | 0534_00000011649 | Wentzo | Hardware and instal. for network & wifi | 85317.5 | 85317.5 | 0 | 85317.5 | 5011.86 | 90329.36 | 1 | 1 | 1 | 1 | 1 | 61451.5
112 | 2026-04-30 | 2026-04-30 | VMI26_00214 | Artelia /Stylt | Phase 5 | 7950 | 7950 | 0 | 7950 | 0 | 7950 | 1 | 1 | 1 |  | 0 | 0
113 | 2026-04-30 | 2026-04-30 | VMI26_00222 | Artelia /Stylt | Phase 5 | 1650 | 1650 | 0 | 1650 | 0 | 1650 | 1 | 1 | 1 |  |  | 0
114 | 2026-04-30 | 2026-04-30 | VMI26_00201 | Artelia | Project Management | 11426.087 | 11426.14 | 0 | 11426.14 | 0 | 11426.14 | 1 | 0 | 0 |  | 0 | 0
115 | 2026-04-30 | 2026-04-30 | VMI26_00201 | Artelia | Construction Management | 3130.4348 | 3130.56 | 0 | 3130.56 | 0 | 3130.56 | 1 | 0 | 0 |  | 0 | 0
116 | 2026-04-30 | 2026-04-30 | VMI26_00201 | Artelia | Direzione Lavori | 6480 | 6230.77 | 249.2308 | 6480.0008 | 0 | 6480.0008 | 1 | 0 | 0 |  | 0 | 0
117 | 2026-04-30 | 2026-04-30 | VMI26_00201 | Artelia | Health & Safety | 4320 | 4153.85 | 166.154 | 4320.004 | 0 | 4320.004 | 1 | 0 | 0 |  | 0 | 0
118 | 2026-04-30 | 2026-04-30 | VMI26_00201 | Artelia | ID Coordination | 869.5652 | 869.43 | 0 | 869.43 | 0 | 869.43 | 1 | 0 | 0 |  | 0 | 0
119 | 2026-04-30 | 2026-04-30 | XXXX | Protos | Monitoring | 2700 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0
120 | 2026-04-30 | 2026-04-30 | XXXX | Catalyst | Flood risk ass.+Resources Inv.services | 9000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0
Formulas:
EOMONTH = EOMONTH([Invoice Date],0)

## Model - Capex (hidden)
To Date | 2026-03-31
Period |  | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
BoP |  | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2025-01-01 | 2025-04-01 | 2025-07-01 | 2025-10-01 | 2026-01-01 | 2026-04-01 | 2026-07-01 | 2026-10-01 | 2027-01-01 | 2027-04-01 | 2027-07-01
EoP | Total | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2025-03-31 | 2025-06-30 | 2025-09-30 | 2025-12-31 | 2026-03-31 | 2026-06-30 | 2026-09-30 | 2026-12-31 | 2027-03-31 | 2027-06-30 | 2027-09-30
Paid | 840931.244 | 0 | 4000 | 5100 | 0 | 64200 | 173392.79 | 16000 | 6802 | 329705.8261 | 16498.087 | 47974.087 | 11936.24 | 2052.02 | 163270.194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9100 | -237592.79 | -352507.8261 | -76408.4139 | -165322.214 | 0 | 0 | 0 | 0 | 0 | 0 | -840931.244
VAT | 182741.0989 | 0 | 0 | 572 | 0 | 14124 | 38146.4138 | 3520 | 0 | 74161.1774 | 3393.7391 | 10116.9391 | 2619.3728 | 168.014 | 35919.4427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -572 | -52270.4138 | -77681.1774 | -16130.0511 | -36087.4567 | 0 | 0 | 0 | 0 | 0 | 0 | -182741.0989
Gross Paid | 1023672.3429 | 0 | 4000 | 5672 | 0 | 78324 | 211539.2038 | 19520 | 6802 | 403867.0035 | 19891.8261 | 58091.0261 | 14555.6128 | 2220.034 | 199189.6367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -9672 | -289863.2038 | -430189.0035 | -92538.465 | -201409.6707 | 0 | 0 | 0 | 0 | 0 | 0 | -1023672.3429
Artelia Forecast | 7343224.9786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598243.0839 | 680821.7799 | 770821.7799 | 766417.3299 | 682774.6599 | 795274.6599 | 810274.6599 | 831274.6599 | 649195.9639 | 758126.4019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Total | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.147% | 9.271% | 10.5% | 10.44% | 9.298% | 10.83% | 11.03% | 11.32% | 8.841% | 10.32% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
% Total - Forecast Curve | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.147% | 9.271% | 10.5% | 10.44% | 9.298% | 10.83% | 11.03% | 11.32% | 8.841% | 10.32% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Remaining Spend | 7859068.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640268.2122 | 728647.8617 | 824970.1438 | 820256.2918 | 730737.9268 | 851140.7794 | 867194.4931 | 889669.6923 | 694800.4087 | 811382.9462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2193886.2177 | -2402134.998 | -2451664.594 | -811382.9462 | 0 | 0 | -7859068.756
VAT (Assumption) | 1728995.1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140859.0067 | 160302.5296 | 181493.4316 | 180456.3842 | 160762.3439 | 187250.9715 | 190782.7885 | 195727.3323 | 152856.0899 | 178504.2482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -482654.9679 | -528469.6996 | -539366.2107 | -178504.2482 | 0 | 0 | -1728995.1263
Remaining + VAT | 9588063.8823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781127.2189 | 888950.3913 | 1006463.5754 | 1000712.6761 | 891500.2707 | 1038391.7509 | 1057977.2816 | 1085397.0246 | 847656.4986 | 989887.1944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2676541.1856 | -2930604.6976 | -2991030.8047 | -989887.1944 | 0 | 0 | -9588063.8823
Model - Dev Costs | 7859068.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640268.2122 | 728647.8617 | 824970.1438 | 820256.2918 | 730737.9268 | 851140.7794 | 867194.4931 | 889669.6923 | 694800.4087 | 811382.9462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2193886.2177 | -2402134.998 | -2451664.594 | -811382.9462 | 0 | 0 | -7859068.756
Model - VAT Due | 1728995.1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140859.0067 | 160302.5296 | 181493.4316 | 180456.3842 | 160762.3439 | 187250.9715 | 190782.7885 | 195727.3323 | 152856.0899 | 178504.2482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -482654.9679 | -528469.6996 | -539366.2107 | -178504.2482 | 0 | 0 | -1728995.1263
Model - VAT Repaid | -1728995.1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -140859.0067 | -160302.5296 | -181493.4316 | -180456.3842 | -160762.3439 | -187250.9715 | -190782.7885 | -195727.3323 | -152856.0899 | -178504.2482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482654.9679 | 528469.6996 | 539366.2107 | 178504.2482 | 1728995.1263
[35 empty] | 0.1046% | 2.731% | 4.052% | 0.8783% | 1.9% | 25.22% | 27.61% | 28.18% | 9.326%
Note on D15: As per Q4 2025 - assumed we not use 300k EUR of contingency and therefore deducted from the budget

## Model - Preopening & Fees
Florence - Preopening Budget
Actuals To Date | [6 empty] | 2026-06-30
Period | [7 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 8 | 8 | 9 | 9 | 9 | 10 | 10 | 10 |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
BoP | [7 empty] | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 |  | 2025-01-01 | 2025-04-01 | 2025-07-01 | 2025-10-01 | 2026-01-01 | 2026-04-01 | 2026-07-01 | 2026-10-01 | 2027-01-01 | 2027-04-01 | 2027-07-01
EoP | [6 empty] | Total | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 |  | 2025-03-31 | 2025-06-30 | 2025-09-30 | 2025-12-31 | 2026-03-31 | 2026-06-30 | 2026-09-30 | 2026-12-31 | 2027-03-31 | 2027-06-30 | 2027-09-30
Marketing
Budget | Description | Bucket | Owner | Budget | Spent | Remaining
PR & Communications
Communication Plan (with Local Agency) |  | Marketing | Aniek | 20000 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -20000 | 0 | 0 | 0 | 0 | -20000
PR (with Local Agency) year retainer |  | Marketing | Aniek | 26500 | 0 | 26500 | 26500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -4000 | -6000 | -6500 | -7500 | -2500 | -26500
Photo & Video
Photoshoot September - Mock Up Rooms |  | Marketing | Aniek | 3000 | 1000 | 2000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -1000 | 0 | 0 | -2000 | 0 | 0 | 0 | 0 | -3000
Photoshoot Full February |  | Marketing | Aniek | 4000 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4000 | 0 | 0 | -4000
Videoshoot (included in Diginauts scope) |  | Marketing | Aniek | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Videoshoot Lifestyle February |  | Marketing | Aniek | 4000 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Photoshoot Lifestyle & City February |  | Marketing | Aniek | 4000 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F&B - Il Solito Branding
Visual Identity Development (Logo, Fonts, Guidelines) |  | Marketing | Aniek | 15000 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -15000 | 0 | 0 | 0 | 0 | -15000
Photography F&B |  | Marketing | Aniek | 2000 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2000 | 0 | 0 | -2000
Social Media
Influencer Fees |  | Marketing | Aniek | 13200 | 0 | 14200 | 14200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 4400 | 4500 | 3000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6700 | -7500 | 0 | -14200
Boosting Organic Content |  | Marketing | Aniek | 1600 | 0 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -600 | -600 | -400 | 0 | -1600
Online Marketing / Paid Media
Diginauts Retainer (Sep 2026 till April 2027) |  | Marketing | Aniek | 7832 | 0 | 7862 | 7862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 460 | 1157 | 1157 | 1157 | 1157 | 1157 | 1157 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | -460 | -2774 | -3471 | -1157 | 0 | -7862
Room Ads |  | Marketing | Aniek | 21056 | 0 | 21056 | 21056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 883 | 883 | 2038 | 2038 | 4347 | 4347 | 6520 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3804 | -10732 | -6520 | 0 | -21056
F&B Ads |  | Marketing | Aniek | 2309 | 0 | 2309 | 2309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 272 | 543 | 543 | 815 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -136 | -1358 | -815 | 0 | -2309
Branded Ads |  | Marketing | Aniek | 3802 | 0 | 3802 | 3802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475 | 475 | 543 | 408 | 543 | 543 | 815 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1493 | -1494 | -815 | 0 | -3802
See this doc for split per channel |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Printed Materials & Advertising
Production Campaign Materials (OOH, Guerilla) |  | Marketing | Aniek | 25000 | 0 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 10000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | -15000 | -5000 | 0 | -25000
Print Materials (excl. build & ops/F&B & recruitment materials) |  | Marketing | Aniek | 5000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3500 | -1500 | 0 | -5000
Website & Content
Miscellaneous (Illustrations, IBE tbc) |  | Marketing | Aniek | 3000 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3000 | 0 | 0 | 0 | -3000
[42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opening Party / Launch Event
Partner Fees |  | Marketing | Aniek | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3750 | -3750 | 0 | -7500
F&B Events |  | Marketing | Aniek | 5000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -5000 | 0 | -5000
Equipment Events |  | Marketing | Aniek | 2000 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2000 | 0 | -2000
Gifting |  | Marketing | Aniek | 5000 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2500 | -2500 | 0 | -5000
Photography Events |  | Marketing | Aniek | 2000 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2000 | 0 | -2000
Total Marketing |  |  |  | 182799 | 1000 | 182829 | 183829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 9500 | 4460 | 7018 | 9715 | 6074 | 13575 | 37090 | 18940 | 38257 | 5700 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | -1000 | 0 | 0 | -41460 | -22807 | -61605 | -46457 | -2500 | -175829
1000
Legal
Budget |  | Bucket |  | Budget | Spent | Remaining
Contracts Review and Advice |  | Legal | Kim | 0 | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1800
Construction Agreement |  | Legal | Kim | 20000 | 29500 | 0 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -29500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29500
Template FF&E contracts |  | Legal | Kim | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assistance in the FF&E construction agreement with Factory and Senci |  | Legal | Kim | 6835.5 | 6835.5 | 4000 | 10835.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6835.5 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -6835.5 | 0 | -4000 | 0 | 0 | 0 | 0 | -10835.5
Legal Support Contracts during 2026 |  | Legal | Kim | 12000 | 0 | 9500 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1500 | 1500 | 1500 | 1500 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -3500 | -4000 | -2000 | 0 | 0 | -9500
Corporate Work to Date |  | Legal | Kim | 17164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corporate Work 2026 (if necessary) |  | Legal | Kim | 12000 | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 1500 | 1500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -5500 | -2500 | -1000 | 0 | 0 | -9000
Second opinion related to labour and employment pre closing Hotel Corona |  | Legal | Kim | 4000 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1000 | 1000 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3500 | -500 | 0 | 0 | -4000
Contingency/Italian law queries during the construction phase Jan-Dec 2026 |  | Legal | Kim | 7000 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -1500 | -1500 | -1000 | 0 | 0 | -4000
Total Legal |  |  |  | 82999.5 | 38135.5 | 30500 | 68635.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31300 | 0 | 0 | 6835.5 | 0 | 0 | 0 | 5000 | 6000 | 3500 | 5000 | 3500 | 3000 | 2500 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -31300 | -6835.5 | 0 | -14500 | -11500 | -4500 | 0 | 0 | -68635.5
HR
Budget |  | Bucket |  | Budget | Spent | Remaining
Pre-Opening Training & Compliance Budget
Mandatory Compliance Training |  | HR | Joyce | 16800 | 0 | 12800 | 12800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10000 | -2800 | 0 | 0 | -12800
External Meeting Room & Lunch (2 weeks) |  | HR | Joyce | 16000 | 0 | 16000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 4000 | 4000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -11000 | -5000 | 0 | 0 | -16000
Travel Costs - Shadow Shifts Leadership Team Florence |  | HR | Joyce | 1500 | 345.89 | 2000 | 2345.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288.79 | 0 | 0 | 57.1 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -288.79 | -57.1 | 0 | -1000 | -1000 | 0 | 0 | -2345.89
Recruitment Budget
Social Media Recruitment - Tiktok & Meta (Instagram) Ads Daily Budget of €100-€150 recommended for enough visibility. 2x to run different ads (for F&B & front office) |  | HR | Joyce | 3500 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 500 | 1500 | 1000 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -500 | -3000 | 0 | 0 | 0 | -3500
LinkedIn & Indeed Promotions to be used for specialist roles, e.g. chef, hotel manager, F&B MOD |  | HR | Joyce | 2000 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 500 | 500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -1500 | -500 | 0 | 0 | 0 | -2000
Offline Visibility - e.g. campaign materials limited - more focus on online visibility to reach target audience |  | HR | Joyce | 2500 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2000 | -500 | 0 | 0 | -2500
In-house Recruitment Day |  | HR | Joyce | 7500 | 789.8 | 7500 | 8289.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789.8 | 0 | 0 | 0 |  | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -789.8 | 0 | -7500 | 0 | 0 | 0 | -8289.8
Staff Costs Pre-Opening
Ongoing Salary Andi - Reception Manager |  | HR | Joyce | 46702 | 12737 | 33965.3333 | 46702.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4245.6667 | 4245.6667 | 4245.6667 | 4245.6667 | 4245.6667 | 4245.6667 | 4245.6667 | 4245.6667 | 4245.6667 | 4245.6667 | 4245.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -12737 | -12737 | -12737 | -8491.3333 | 0 | 0 | -46702.3333
Hotel Manager - Fabio |  | HR | Joyce | 40000 | 0 | 45833.3333 | 45833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9166.6667 | 9166.6667 | 9166.6667 | 9166.6667 | 9166.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -27500 | -18333.3333 | 0 | 0 | -45833.3333
Staff Costs Preopening (23 FTE) - excl. Fabio & Andi |  | HR | Joyce | 60000 | 0 | 49000 | 49000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 10000 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4000 | -45000 | 0 | 0 | -49000
Sales Manager External - Preopening Push |  | HR | Joyce | 15000 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 2200 | 2200 | 2200 | 2200 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -2200 | -6600 | -4400 | 0 | 0 | -13200
Sales Representation APLBC |  | HR | Joyce | 18000 | 2000 | 16000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -2000 | -6000 | -6000 | -4000 | 0 | 0 | -18000
Reorganisation former hotel team
TFR Costs Reorganisation |  | HR | Joyce | 198984 | 57893 | 141091 | 198984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57893 | 0 | 0 | 0 | 141091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -57893 | 0 | -141091 | 0 | 0 | 0 | 0 | -198984
Settlement Costs Staff Reorganisation |  | HR | Joyce | 166966 | 166966 | 38776 | 205742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166966 | 0 | 0 | 0 | 38776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -166966 | 0 | -38776 | 0 | 0 | 0 | 0 | -205742
Legal Costs - Studio Pirola Reorganisation |  | HR | Joyce | 25000 | 12000 | 8000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -12000 | 0 | 0 | -8000 | 0 | 0 | 0 | 0 | -20000
Total HR |  |  |  | 620452 | 252731.69 | 392165.6667 | 644897.3567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 225147.79 | 4245.6667 | 5035.4667 | 6302.7667 | 191112.6667 | 10245.6667 | 9445.6667 | 25862.3333 | 30862.3333 | 35112.3333 | 36912.3333 | 52612.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -288.79 | -15583.9 | -22937 | -91837 | -89524.6667 | 0 | 0 | -220171.3567
IT Systems
Budget |  | Bucket |  | Budget | Spent | Remaining
IT - Administrative & General (Exact, Keeper, Oneteam, Office365) |  | IT | Marc | 8000 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4000 | -4000 | 0 | 0 | -8000
IT - Food & Beverage |  | IT | Marc | 3900 | 0 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2700 | -1200 | 0 | 0 | -3900
IT - Human Resources (Personio, Shiftbase) |  | IT | Marc | 2000 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1000 | -1000 | 0 | 0 | -2000
IT - Others (Mosyle, Reviewpro, MS Defender) |  | IT | Marc | 600 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200 | -400 | 0 | 0 | -600
IT - Rooms (D3x, Apaleo, Zaplox, Siteminder, Flyr, Sweeply, Lighthouse, Hibox, Boookboost) |  | IT | Marc | 17600 | 0 | 17600 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 3200 | 3200 | 3200 | 3200 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -1600 | -9600 | -6400 | 0 | 0 | -17600
IT - Sales & Marketing (Cendyn, MIG and Semrush) |  | IT | Marc | 2700 | 0 | 2700 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 450 | 450 | 450 | 450 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -450 | -1350 | -900 | 0 | 0 | -2700
Contract services |  | IT | Marc | 400 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -400 | 0 | 0 | -400
TV |  | IT | Marc | 300 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -300 | 0 | 0 | -300
Internet & Telecom |  | IT | Marc | 6300 | 0 | 6300 | 6300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2100 | -4200 | 0 | 0 | -6300
Software Licences (phished, io) |  | IT | Marc | 510 | 0 | 510 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 170 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -170 | -340 | 0 | 0 | -510
Total IT systems |  |  |  | 42310 | 0 | 42310 | 42310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 3650 | 8250 | 9220 | 9570 | 9570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -2050 | -21120 | -19140 | 0 | 0 | -42310
OS&E
Budget |  | Bucket |  | Budget | Spent | Remaining
Complete OS&E and operations supply list (see separate list) |  | OS&E | Michiel | 170000 | 0 | 170000 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 10000 | 20000 | 20000 | 30000 | 40000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -35000 | -90000 | -45000 | 0 | 0 | -170000
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total OS&E |  |  |  | 170000 | 0 | 170000 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 10000 | 20000 | 20000 | 30000 | 40000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -35000 | -90000 | -45000 | 0 | 0 | -170000
Other Costs
Budget |  | Bucket |  | Budget | Spent | Remaining
Working Capital - F&B inventory (food, beverages, grab&go) |  | Other Costs | Michael | 40000 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -40000 | 0 | 0 | -40000
Working Capital - Room inventory (toilet paper, coffee, tea etc) |  | Other Costs | Joachim | 3500 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3500 | 0 | 0 | -3500
Working Capital - Preopening Deep Clean (guestrooms & public areas) |  | Other Costs | Joachim | 25000 |  | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel Costs UHG / Support Team - Flights & Hotel Stays |  | Other Costs | Joachim | 40000 | 2364 | 30000 | 32364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2364 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1500 | 1500 | 2000 | 3000 | 5000 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -2364 | 0 | 0 | -6000 | -10000 | -14000 | 0 | 0 | -32364
F&B Consultant - EME Consultancy |  | Other Costs | Joachim | 76800 | 15235.03 | 51200 | 66435.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8835.03 | 6400 | 6400 | 6400 | 6400 | 6400 | 6400 | 6400 | 6400 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | -15235.03 | -19200 | -19200 | -12800 | 0 | 0 | -66435.03
OS&E Consultant |  | Other Costs | Michiel | 7500 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -1500 | -4500 | -1500 | 0 | 0 | -7500
Total Other Costs |  |  |  | 192800 | 17599.03 | 162200 | 179799.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2364 | 0 | 0 | 0 | 0 | 8835.03 | 6400 | 9400 | 7900 | 9400 | 9900 | 10900 | 12900 | 45400 | 56400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -2364 | 0 | -15235.03 | -26700 | -33700 | -71800 | 0 | 0 | -149799.03
Preopening Cost Summary
Budget |  | Bucket |  | Budget | Spent | Remaining
Marketing |  | Marketing | Aniek | 182799 | 1000 | 182829 | 183829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 9500 | 4460 | 7018 | 9715 | 6074 | 13575 | 37090 | 18940 | 38257 | 5700 | 2500 | 2500 | 0 | 0 |  | 0 | 0 | 0 | -1000 | 0 | 0 | -41460 | -22807 | -61605 | -46457 | -2500 | -175829
Legal |  | Legal | Kim | 82999.5 | 38135.5 | 30500 | 68635.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31300 | 0 | 0 | 6835.5 | 0 | 0 | 0 | 5000 | 6000 | 3500 | 5000 | 3500 | 3000 | 2500 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -31300 | -6835.5 | 0 | -14500 | -11500 | -4500 | 0 | 0 | -68635.5
HR |  | HR | Joyce | 620452 | 252731.69 | 392165.6667 | 644897.3567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 225147.79 | 4245.6667 | 5035.4667 | 6302.7667 | 191112.6667 | 10245.6667 | 9445.6667 | 25862.3333 | 30862.3333 | 35112.3333 | 36912.3333 | 52612.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -288.79 | -15583.9 | -22937 | -91837 | -89524.6667 | 0 | 0 | -220171.3567
IT |  | IT | Marc | 42310 | 0 | 42310 | 42310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2050 | 3650 | 8250 | 9220 | 9570 | 9570 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OS&E |  | OS&E | Michiel | 170000 | 0 | 170000 | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 10000 | 20000 | 20000 | 30000 | 40000 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -35000 | -90000 | -45000 | 0 | 0 | -170000
Other Costs |  | Other Costs | Joachim/Michiel | 192800 | 17599.03 | 162200 | 179799.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2364 | 0 | 0 | 0 | 0 | 8835.03 | 6400 | 9400 | 7900 | 9400 | 9900 | 10900 | 12900 | 45400 | 56400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | -2364 | 0 | -15235.03 | -26700 | -33700 | -71800 | 0 | 0 | -149799.03
Total Preopening Cost |  |  |  | 1291360.5 | 309466.22 | 980004.6667 | 1289470.8867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46664 | 0 | 0 | 231983.29 | 4245.6667 | 13870.4967 | 12702.7667 | 238012.6667 | 43645.6667 | 48855.6667 | 71430.3333 | 93227.3333 | 106306.3333 | 152957.3333 | 157672.3333 | 18940 | 38257 | 5700 | 2500 | 2500 | 0 | 0 |  | 0 | 0 | 0 | -34664 | -7124.29 | -30818.93 | -140597 | -249844 | -272429.6667 | -46457 | -2500 | -784434.8867
-1889.6133
UHG Fees
Budget |  | Bucket |  | Budget | Spent | Remaining
DM Fee |  | UHG Fees | Michiel / Joachim | 360000 | 266156.25 | 93843.75 | 360000 | 97000 | 0 | 0 | 97000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11750 | 11750 | 11750 | 11750 | 11750 | 13406.25 | 13406.25 | 13406.25 | 13406.25 | 13406.25 | 13406.25 | 13406.25 | 13406.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -97000 | -97000 | 0 | 0 | -35250 | -36906.25 | -40218.75 | -40218.75 | -13406.25 | 0 | 0 | -360000
Preopening Fee |  | UHG Fees | Joachim | 60000 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | -24000 | -36000 | 0 | 0 | 0 | -60000
Total UHG Fees |  |  |  | 420000 | 266156.25 | 153843.75 | 420000 | 97000 | 0 | 0 | 97000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11750 | 11750 | 11750 | 11750 | 11750 | 13406.25 | 13406.25 | 25406.25 | 25406.25 | 25406.25 | 25406.25 | 25406.25 | 13406.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -97000 | -97000 | 0 | 0 | -35250 | -36906.25 | -64218.75 | -76218.75 | -13406.25 | 0 | 0 | -420000
Other Costs - Not In Budget
Budget |  | Bucket |  | Budget | Spent | Remaining
Deloitte |  | Other Costs - Not In Budget |  | 0 | 70160.98 | 0 | 70160.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70160.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -70160.98 | 0 | 0 | 0 | 0 | 0 | 0 | -70160.98
[Other] |  | Other Costs - Not In Budget |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[Other] |  | Other Costs - Not In Budget |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[Other] |  | Other Costs - Not In Budget |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[Other] |  | Other Costs - Not In Budget |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Other Costs - Not in Budget |  |  |  | 0 | 70160.98 | 0 | 70160.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70160.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -70160.98 | 0 | 0 | 0 | 0 | 0 | 0 | -70160.98
Total Cost Summary
Preopening Costs |  | Preopening Costs |  | 1291360.5 | 309466.22 | 980004.6667 | 1289470.8867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46664 | 0 | 0 | 231983.29 | 4245.6667 | 13870.4967 | 12702.7667 | 238012.6667 | 43645.6667 | 48855.6667 | 71430.3333 | 93227.3333 | 106306.3333 | 152957.3333 | 157672.3333 | 18940 | 38257 | 5700 | 2500 | 2500 | 0 | 0
UHG Fees |  | UHG Fees |  | 420000 | 266156.25 | 153843.75 | 420000 | 97000 | 0 | 0 | 97000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11750 | 11750 | 11750 | 11750 | 11750 | 13406.25 | 13406.25 | 25406.25 | 25406.25 | 25406.25 | 25406.25 | 25406.25 | 13406.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -97000 | -97000 | 0 | 0 | -35250 | -36906.25 | -64218.75 | -76218.75 | -13406.25 | 0 | 0 | -420000
Other Costs - Not In Budget |  | Other Costs - Not In Budget |  | 0 | 70160.98 | 0 | 70160.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70160.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | -70160.98 | 0 | 0 | 0 | 0 | 0 | 0 | -70160.98
Total Cost |  |  |  | 1711360.5 | 645783.45 | 1133848.4167 | 1779631.8667 | 97000 | 0 | 0 | 97000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46664 | 11750 | 11750 | 313894.27 | 15995.6667 | 25620.4967 | 26109.0167 | 251418.9167 | 69051.9167 | 74261.9167 | 96836.5833 | 118633.5833 | 131712.5833 | 166363.5833 | 157672.3333 | 18940 | 38257 | 5700 | 2500 | 2500 | 0 | 0 |  | -97000 | -97000 | 0 | 0 | -175571.96 | -36906.25 | -64218.75 | -76218.75 | -13406.25 | 0 | 0 | -560321.96
23517.5533
Note on X92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Notice in lieu of notice (Mancato Preavviso Ditta), excl. employer contributions. Was included in January 2026 payroll.
Note on Z92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Joyce Hilders Kosten updaten, met kosten tot nu toe gemaakt en wat er overblijft kosten die we nog verwachten en in welke maand
Note on B96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Marc Laros Hi Marc, dit is het stuk voor jou om aan te vullen voor alle IT kosten die niet in het OS&E budget staan

## Summary
|  | UW Budget | Revised Budget
Preopening Budget - Overview | Department | UW | Original UHG Budget | Spent | Remaining | Total Forecast Spend | Over / (Under) Original UHG Budget
Marketing | Marketing | 150000 | 215799 | 3000 | 212029 | 215029 | -770
Legal | Legal | 0 | 82999.5 | 38135.5 | 30500 | 68635.5 | -14364
HR - Preopening Recruiting, Staffing & Training | HR | 65161.2723 | 196502 | 13872.69 | 175098.6667 | 188971.3567 | -7530.6433
HR - Staff Reorganisation | HR | 373000 | 390950 | 236859 | 187867 | 424726 | 33776
IT Systems | IT | 0 | 42310 | 0 | 42310 | 42310 | 0
OS&E | Development | 0 | 170000 | 0 | 170000 | 170000 | 0
Working Capital | Other | 81000 | 68500 | 0 | 73500 | 73500 | 5000
Travel Costs (UHG) | Other | 0 | 40000 | 2364 | 30000 | 32364 | -7636
F&B Consultant - EME Consultancy | F&B | 0 | 76800 | 15235.03 | 51200 | 66435.03 | -10364.97
OS&E Consultant | Development | 0 | 7500 | 0 | 7500 | 7500 | 0
Total |  | 669161.2723 | 1291360.5 | 309466.22 | 980004.6667 | 1289470.8867 | -1889.6133
UHG Fees |  |  | 420000 | 266156.25 | 153843.75 | 420000 | 0
Other Costs (not in budget) |  |  | 0 | 70160.98 | 0 | 70160.98 | -70160.98
Total |  |  | 1711360.5 | 645783.45 | 1133848.4167 | 1779631.8667 | -72050.5933
vs Reporting Model | [5 empty] | 1756114.3133
23517.5533

## Invoices - Preopening
Invoice Tracker - Florence Preopening
Yes
Spent To Date |  | 2026-06-30 | [10 empty] | No
Cost Tracker By Bucket |  |  |  | Budget (€) | Spent (€) | Remaining (€) | Amount (€) | VAT (€) | Gross Amount (€)
Marketing |  |  |  | 183829 | 1000 | 182829 | 1000 | 220 | 1220 |  | 0
Legal |  |  |  | 68635.5 | 38135.5 | 30500 | 38135.5 | 8389.81 | 46525.31 |  | 0
HR |  |  |  | 644897.3567 | 252731.69 | 392165.6667 | 252731.69 | 52798.8318 | 305530.5218 |  | 0
IT |  |  |  | 42310 | 0 | 42310 | 0 | 0 | 0
OS&E |  |  |  | 170000 | 0 | 170000 | 0 | 0 | 0 |  | 0
Other Costs |  |  |  | 179799.03 | 17599.03 | 162200 | 17599.03 | 520.08 | 18119.11 |  | 0
UHG Fees |  |  |  | 420000 | 266156.25 | 153843.75 | 266156.25 | 0 | 266156.25 |  | 0
Other Costs - Not In Budget |  |  |  | 70160.98 | 70160.98 | 0 | 70160.98 | 15435.4156 | 85596.3956 |  | 0
Total |  |  |  | 1779631.8667 | 645783.45 | 1133848.4167 | 645783.45 | 77364.1374 | 723147.5874
Total Invoices | [6 empty] | 648819.8 | 78032.1344 | 726851.9344
ID | Bucket (Select Dropdown) | Summary Bucket | Invoice ID | Contractor | Invoice Date | Paid Date | Amount (€) | VAT (€) | Gross Amount (€) | Is this in budget for the scope contracted and the work completed? | Approved - Michiel
1 | Deloitte | Other Costs - Not In Budget | TBC | Deloitte | 2026-03-31 | 2026-03-31 | 70160.98 | 15435.4156 | 85596.3956 | No | No
2 | Travel Costs UHG / Support Team - Flights & Hotel Stays | Other Costs | TBC | UHG | 2025-12-31 | 2025-12-31 | 2364 | 520.08 | 2884.08 | No | No
3 | Legal Costs - Studio Pirola Reorganisation | HR | [ADD] | Studio Pirola | 2025-12-31 | 2025-12-31 | 12000 | 2640 | 14640 | No | No
4 | TFR Costs Reorganisation | HR | [ADD] | [ADD] | 2026-03-31 | 2026-03-31 | 57893 | 12736.46 | 70629.46 | No | No
5 | Settlement Costs Staff Reorganisation | HR | [ADD] | [ADD] | 2026-03-31 | 2026-03-31 | 166966 | 36732.52 | 203698.52 | No | No
6 | Construction Agreement | Legal | [ADD] | Jones Day | 2025-12-31 | 2025-12-31 | 29500 | 6490 | 35990 | No | No
7 | Contracts Review and Advice | Legal | [ADD] | Jones Day | 2025-12-31 | 2025-12-31 | 1800 | 396 | 2196 | No | No
8 | DM Fee | UHG Fees | [ADD] | UHG | 2025-01-31 | 2025-01-31 | 97000 | 0 | 97000 | Yes | No
9 | DM Fee | UHG Fees | [ADD] | UHG | 2025-04-30 | 2025-04-30 | 97000 | 0 | 97000 | Yes | No
10 | DM Fee | UHG Fees | [ADD] | UHG | 2026-01-31 | 2026-01-31 | 11750 | 0 | 11750 | Yes | No
11 | DM Fee | UHG Fees | [ADD] | UHG | 2026-02-28 | 2026-02-28 | 11750 | 0 | 11750 | Yes | No
12 | DM Fee | UHG Fees | [ADD] | UHG | 2026-03-31 | 2026-03-31 | 11750 | 0 | 11750 | Yes | No
13 | DM Fee | UHG Fees | [ADD] | UHG | 2026-04-30 | 2026-04-30 | 11750 | 0 | 11750 | Yes | No
14 | DM Fee | UHG Fees | [ADD] | UHG | 2026-05-31 | 2026-05-31 | 11750 | 0 | 11750 | Yes | No
15 | DM Fee | UHG Fees | [ADD] | UHG | 2026-06-30 | 2026-06-30 | 13406.25 | 0 | 13406.25 | Yes | No
16 | DM Fee | UHG Fees | [ADD] | UHG | [Update] | [Update] | 0 | 0 | 0 | No | No
17 | DM Fee | UHG Fees | [ADD] | UHG | [Update] | [Update] | 0 | 0 | 0 | No | No
18 | DM Fee | UHG Fees | [ADD] | UHG | [Update] | [Update] | 0 | 0 | 0 | No | No
19 | Photoshoot September - Mock Up Rooms | Marketing | [ADD] | Stylt | 2025-12-31 | 2025-12-31 | 1000 | 220 | 1220 | No | No
20 | F&B Consultant - EME Consultancy | Other Costs | [ADD] | EME Hospitality | 2026-05-09 | 2026-05-09 | 8835.03 | 0 | 8835.03 | No | No
21 | F&B Consultant - EME Consultancy | Other Costs | [ADD] | EME Hospitality | 2026-06-03 | 2026-06-03 | 6400 | 0 | 6400 | No | No
22 | Sales Representation APLBC | HR | [ADD] | APLBC | 2026-06-30 | 2026-06-30 | 2000 | 440 | 2440 | No | No
23 | Ongoing Salary Andi - Reception Manager | HR | [ADD] | [ADD] | 2026-04-30 | 2026-04-30 | 4245.6667 | 0 | 4245.6667 | No | No | Check if we have actually paid this
24 | Ongoing Salary Andi - Reception Manager | HR | [ADD] | [ADD] | 2026-05-31 | 2026-05-31 | 4245.6667 | 0 | 4245.6667 | No | No
25 | Ongoing Salary Andi - Reception Manager | HR | [ADD] | [ADD] | 2026-06-30 | 2026-06-30 | 4245.6667 | 0 | 4245.6667 | No | No
26 | Assistance in the FF&E construction agreement with Factory and Senci | Legal | [ADD] | Jones Day | 2026-03-11 | 2026-03-11 | 6835.5 | 1503.81 | 8339.31 | No | No
27 | Photoshoot September - mock up rooms | Marketing | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
28 | Travel Costs - Shadow Shifts Leadership Team Florence | HR | [ADD] | KLM | 2026-03-11 | 2026-03-11 | 180.98 | 39.8156 | 220.7956 | Yes | No
29 | Travel Costs - Shadow Shifts Leadership Team Florence | HR | [ADD] | Vueling | 2026-03-11 | 2026-03-11 | 107.81 | 23.7182 | 131.5282 | Yes | No
30 | In-house Recruitment Day | HR | [ADD] | KLM | 2026-05-29 | 2026-05-29 | 495.8 | 109.076 | 604.876 | Yes | No
31 | In-house Recruitment Day | HR | [ADD] | KLM | 2026-05-29 | 2026-05-29 | 294 | 64.68 | 358.68 | Yes | No
32 | Settlement Costs Staff | 0 | [ADD] | AF | 2026-07-02 | 2026-07-08 | 3036.35 | 667.997 | 3704.347 | No | No
33 | Travel Costs - Shadow Shifts Leadership Team Florence | HR | [ADD] | NS international | 2026-06-30 | 2026-06-30 | 8.1 | 1.782 | 9.882 | Yes | No
34 | Travel Costs - Shadow Shifts Leadership Team Florence | HR | [ADD] | NS | 2026-06-30 | 2026-06-30 | 49 | 10.78 | 59.78 | Yes | No
35 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
36 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
37 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
38 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
39 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
40 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
41 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
42 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
43 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
44 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
45 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
46 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
47 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
48 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
49 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
50 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
51 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
52 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
53 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
54 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
55 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
56 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
57 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
58 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
59 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
60 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
61 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
62 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
63 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
64 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
65 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
66 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
67 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
68 |  | 0 | [ADD] | [ADD] | [Update] | [Update] | 0 | 0 | 0 | No | No
Formulas:
Spent (€) = EOMONTH([Spent (€), row above],1)
Remaining (€) = EOMONTH([Remaining (€), row above],1)

## Sheet1 (hidden)
3800
| Preopening Budget | UW | Revised | Delta
| Branding, Sales & Marketng | 150000 | 215029 | 65029
| Staff Reorg | 373000 | #REF! | #REF!
| Pre-opening recruiting, staffing and training | 65161.2723 | #REF! | #REF!
| Legal | 0 | 42135.5 | 42135.5
| Working Capital | 81000 | 40000 | -41000
| OS&E | 0 | 170000 | 170000
| Travel Costs | 0 | 32364 | 32364
| F&B Consultant | 0 | 66435.03 | 66435.03
| OS&E Consultant | 0 | 7500 | 7500
| Deloitte Cost | 0 | 70160.98 | 70160.98
| Total Pre-Opening + Branding | 669161.2723 | #REF! | #REF!
#REF!
1289470.8867
#REF!
| DM Fee + POSA Fee |  | 420000
| incl DM Fee |  | #REF!
| Seed / reporting model budget |  | 1756114.3133

## Data Val (hidden)
Data Validation Input
Communication Plan (with Local Agency) | Marketing
PR (with Local Agency) year retainer | Marketing
Photoshoot September - Mock Up Rooms | Marketing
Photoshoot Full February | Marketing
Videoshoot (included in Diginauts scope) | Marketing
Videoshoot Lifestyle February | Marketing
Photoshoot Lifestyle & City February | Marketing
Visual Identity Development (Logo, Fonts, Guidelines) | Marketing
Photography F&B | Marketing
Influencer Fees | Marketing
Boosting Organic Content | Marketing
Diginauts Retainer (Sep 2026 till April 2027) | Marketing
Room Ads | Marketing
F&B Ads | Marketing
Branded Ads | Marketing
Production Campaign Materials (OOH, Guerilla) | Marketing
Print Materials (excl. build & ops/F&B & recruitment materials) | Marketing
Miscellaneous (Illustrations, IBE tbc) | Marketing
Partner Fees | Marketing
F&B Events | Marketing
Equipment Events | Marketing
Gifting | Marketing
Photography Events | Marketing
Contracts Review and Advice | Legal
Construction Agreement | Legal
Template FF&E contracts | Legal
Assistance in the FF&E construction agreement with Factory and Senci | Legal
Legal Support Contracts during 2026 | Legal
Corporate Work to Date | Legal
Corporate Work 2026 (if necessary) | Legal
Second opinion related to labour and employment pre closing Hotel Corona | Legal
Contingency/Italian law queries during the construction phase Jan-Dec 2026 | Legal
Mandatory Compliance Training | HR
External Meeting Room & Lunch (2 weeks) | HR
Travel Costs - Shadow Shifts Leadership Team Florence | HR
Social Media Recruitment - Tiktok & Meta (Instagram) Ads Daily Budget of €100-€150 recommended for enough visibility. 2x to run different ads (for F&B & front office) | HR
LinkedIn & Indeed Promotions to be used for specialist roles, e.g. chef, hotel manager, F&B MOD | HR
Offline Visibility - e.g. campaign materials limited - more focus on online visibility to reach target audience | HR
In-house Recruitment Day | HR
Ongoing Salary Andi - Reception Manager | HR
Hotel Manager - Fabio | HR
Staff Costs Preopening (23 FTE) - excl. Fabio & Andi | HR
Sales Manager External - Preopening Push | HR
Sales Representation APLBC | HR
TFR Costs Reorganisation | HR
Settlement Costs Staff Reorganisation | HR
Legal Costs - Studio Pirola Reorganisation | HR
IT - Administrative & General (Exact, Keeper, Oneteam, Office365) | IT
IT - Food & Beverage | IT
IT - Human Resources (Personio, Shiftbase) | IT
IT - Others (Mosyle, Reviewpro, MS Defender) | IT
IT - Rooms (D3x, Apaleo, Zaplox, Siteminder, Flyr, Sweeply, Lighthouse, Hibox, Boookboost) | IT
IT - Sales & Marketing (Cendyn, MIG and Semrush) | IT
Contract services | IT
TV | IT | `
Internet & Telecom | IT
Software Licences (phished, io) | IT
Complete OS&E and operations supply list (see separate list) | OS&E
Working Capital - F&B inventory (food, beverages, grab&go) | Other Costs
Working Capital - Room inventory (toilet paper, coffee, tea etc) | Other Costs
Working Capital - Preopening Deep Clean (guestrooms & public areas) | Other Costs
Travel Costs UHG / Support Team - Flights & Hotel Stays | Other Costs
F&B Consultant - EME Consultancy | Other Costs
OS&E Consultant | Other Costs
DM Fee | UHG Fees
Preopening Fee | UHG Fees
Deloitte | Other Costs - Not In Budget
[Other] | Other Costs - Not In Budget
[Other] | Other Costs - Not In Budget
[Other] | Other Costs - Not In Budget
[Other] | Other Costs - Not In Budget